## Timeline
Week | Tasks | Lead | Deliverables / Notes
Week 1 | • Kickoff Meeting with Client • Discovery: brand, goals, audiences • Initial Brand Audit | Both | Meeting summary, brand audit notes
| • Gather content/assets from client (images, service list, etc.) | Both | Google Drive folders set up
| • Sitemap draft for website | Carlos | Initial sitemap w/ segmentation
Week 2 | • Define brand positioning, audience segments, voice | Naisargi | Draft brand messaging framework
| • Build website wireframes (desktop + mobile) | Carlos | 2–3 layout options for homepage and service pages
| • Instagram profile audit + bio rewrite | Naisargi | Optimized profile text, bio links
Week 3 | • Finalize brand guide (fonts, tone, colors) | Naisargi | Visual style guide PDF
| • Copywriting for website begins | Carlos | Home, About, Service sections copy
| • Build 1-month content calendar (social) | Naisargi | 12 post ideas + captions
Week 4 | • Design social templates (Reels, Carousels, Story sets) | Naisargi | Canva templates ready to populate
| • Begin development of website (desktop/mobile) | Carlos | Homepage + 1-2 internal pages (HTML/CMS or handoff)
| • Finalize and organize social media assets | Naisargi | Preload Week 5–6 content
Week 5 | • Finish website development (pages + forms) | Carlos | All primary site pages ready for review
| • Set up Google Analytics & Tag Manager | Carlos | Tracking for CTAs, forms, and traffic
| • Keyword research + SEO meta writing | Carlos | 5–10 key pages optimized
Week 6 | • Website QA & feedback revisions | Carlos | Client review & adjustments
| • Begin posting to Instagram (Week 1–2 of calendar) | Naisargi | 3–4 posts/week
| • Launch lead gen funnel & forms | Carlos | CTA testing, simple thank-you pages
Week 7 | • Social media ad audience plan (optional) | Naisargi | Define audiences & test budget plan
| • Publish final website live | Carlos | Confirm mobile, forms, tracking, speed
Week 8 | • Share performance dashboard setup (GA, IG insights) | Carlos | Monthly reporting template
| • Handoff brand & content files to client | Both | All work packaged into Google Drive
| • Final recap meeting | Both | Wins, next steps, support plan (if retained)